## Action Items
Action Item | Responsible | Status | Start date | Due Date | # | Full name | Student ID | Account | Role
Complete SRS Document | PM, BE, BA | Completed | 2025-01-06 | 2025-01-12 | 1 | Lê Minh Vương | QE170148 | VuongLM | PM, BE, FE
Design UI Wireframes | DS | Completed | 2025-01-13 | 2025-01-19 | 2 | Nguyễn Thị Thúy | QE170033 | ThuyNT | QA, FE
Backend API Development | BE | Completed | 2025-01-20 | 2025-02-02 | 3 | Đinh Quốc Chương | QE170097 | ChuongDQ | BE, FE
Frontend Development & Integrate API | FE | Completed | 2025-02-03 | 2025-03-09 | 4 | Hồ Trọng Nghĩa | QE170173 | NghiaHT | DS, FE
Deployment to Cloud | BE | Completed | 2025-03-10 | 2025-03-16 | 5 | Lâm Mỹ Linh | QE170023 | LinhLM | BA, FE
Complete User Documentation | Whole team | Completed | 2025-03-17 | 2025-03-27 | 6 | Lê Mạnh Hùng | QE170213 | HungLM | DS, FE

## Planning
Phase | Timeframe | Goal | Main Tasks | Description | Responsible | Tools | Outputs
Planning & Design | Week 1-2 | Finalize SRS, architecture, and prototypes | SRS Document | Finalize functional and non-functional requirements, including system models. | PM, BA, BE | Google Docs, ClickUp, Lucidchart | Finalized SRS, system models, project roadmap
|  |  | System Design Specification (SDS) | Define overall architecture, components, data flow, and API design. | PM, BE | Lucidchart, Google Docs | SDS document
|  |  | UI/UX Design | Create wireframes and mockups for key interfaces (Home, Course Page, Dashboard). | DS | Figma, Adobe XD | Wireframes, mockups for main screens
|  |  | Tech Selection | Finalize backend, frontend frameworks (NestJS, Next.js), database (PostgreSQL), and cloud provider. | PM, BE, FE | Google Sheets | Tech stack decision matrix
|  |  | Database Design | Design database schema with tables for Users, Courses, Payments, and Progress Tracking. | BE | Lucidchart, dbdiagram.io | Database ERD diagram
Development | Week 3 | Build foundational backend and frontend | Backend APIs, frontend layout, CI/CD pipelines | Develop initial backend (NestJS), frontend (Next.js). Create user registration, login, and database schema for key entities. | BE, FE, QA, PM | NestJS, Next.js, Vercel, Prisma | Functional login and user registration features
| Week 4 | Develop user-centric features | Build core user workflows: course listing, enrollment, progress tracking. | Implement core features for user profiles, course listing, and enrollment system. | BE, FE, QA | Postman, Swagger, Supabase, Stripe | Core features for user management and course workflows
| Week 5 | Integrate core features | API integration, payment systems, UI polish | Integrate backend APIs with the frontend. Add payment workflows (Stripe) and refine dashboard features. | BE, FE, QA | Stripe, SendGrid, Supabase | Working API integrations and payment processing
| Week 6 | Test key workflows | Conduct internal testing for registration, course enrollment, payments, and dashboards. | Test workflows with different roles (User, Lecturer, Admin). Identify and resolve major bugs. | QA, PM, BE | Postman, Jira, Trello | Bug-free workflows for major features
| Week 7 | Enhance features and optimize performance | Add advanced features (e.g., progress tracking visualization), enhance UX/UI, optimize backend. | Refine course progress tracking, UI design, and backend query optimization. | BE, FE, DS, QA | Figma, Prisma, OWASP tools | Enhanced features and optimized system performance
| Week 8 | Perform comprehensive internal testing | Conduct full testing for all modules (Admin, User, Lecturer). Perform stress and security testing. | Test high-load performance, simulate edge cases, ensure security compliance. | QA, PM, BE, FE | Apache JMeter, OWASP tools | Fully tested and secure system ready for deployment
Testing & Deployment | Week 9-10 | Validate system and prepare for launch | Functional Testing | Perform end-to-end testing to ensure feature correctness (registration, course enrollment, payments, etc.). | QA | ClickUp, Postman, AWS | Test case documentation, resolved bugs
|  |  | Performance Testing | Evaluate system performance under high load (up to 100 requests/second). | QA, BE | Apache JMeter, AWS | Performance report
|  |  | Deployment | Deploy application to production environment (AWS, Azure, Vercel, Render). | BE | AWS, Render, Vercel | Live system accessible to users
|  |  | Documentation | Create user guides (Learner, Teacher, Admin) and deployment documentation. | Whole Team | Google Docs, ClickUp | User guides, deployment guide