## Tasks
📝Tasks
COMPLETE
Task ID | Task Name | Assignee | Due Date | Priority | Status
86er83z16 | [BE] Database Design | Quốc Chương - Minh Vương - Trọng Nghĩa | 2025-01-14 | HIGH | COMPLETE
86ermr2tw | [FE] Integrate API Payment for UI Checkout & Learner Purchase History | Mỹ Linh | 2025-02-28 | URGENT | COMPLETE
86ernx5ka | [FE] Integrate API Become a Teacher | Mỹ Linh | 2025-03-02 | URGENT | COMPLETE
86er8ktx0 | [BE] Implement Prisma for login/register UCs | Minh Vương | 2025-01-11 | HIGH | COMPLETE
86era70cm | [BE] Implement CRUD for Admin | Minh Vương | 2025-01-20 | URGENT | COMPLETE
86er9h7p4 | [Deploy] Setup infrastructure | Minh Vương | 2025-01-19 | HIGH | COMPLETE
86er85yj5 | [FE] Install necessary packages | Minh Vương | 2025-01-15 | HIGH | COMPLETE
86er85yg1 | [BE] Install necessary packages | Minh Vương | 2025-01-15 | HIGH | COMPLETE
86er70209 | [DOCS] Requirement Analyzis | Mỹ Linh - Thị Thúy | 2025-01-12 10:00 | URGENT | COMPLETE
86er70d8r | [BE] Setup project base | Minh Vương | 2025-01-11 | HIGH | COMPLETE
86er70d78 | [FE] Setup project base | Minh Vương | 2025-01-11 | HIGH | COMPLETE
86er7enre | [DEPLOYMENT] Initial Backend | Quốc Chương | 2025-01-10 | NORMAL | COMPLETE
86er7enup | [DEPLOYMENT] Initial Frontend | Quốc Chương | 2025-01-10 | NORMAL | COMPLETE
86er70c8q | [FE] UI/UX Design | Trọng Nghĩa - Mạnh Hùng | 2025-01-13 10:00 | HIGH | COMPLETE
86er84bgy | [DOCS] Add Database Design Detail | Trọng Nghĩa - Mạnh Hùng | 2025-01-12 22:00 | NORMAL | COMPLETE
86er84a69 | [DOCS] Project Planning | Quốc Chương | 2025-01-13 | URGENT | COMPLETE
86er8ehnh | [DOCS] Define list of Use case in system | Trọng Nghĩa - Thị Thúy - Mạnh Hùng - Mỹ Linh | 2025-01-13 22:00 | HIGH | COMPLETE
86er8w3ky | [FE] setup base code structure | Quốc Chương | 2025-01-15 | HIGH | COMPLETE
86er8mehb | [DOCS] Create Learner UCs: Register - Login & Logout (Clerk) | Trọng Nghĩa | 2025-01-18 | URGENT | COMPLETE
86er8mez9 | [DOCS] Create Admin UCs: Login | Thị Thúy | 2025-01-18 | URGENT | COMPLETE
86er8merk | [DOCS] Create Teacher UCs: Register - Login & Logout (Clerk) | Mạnh Hùng | 2025-01-18 | URGENT | COMPLETE
86er96x6w | [DOCS] Create Teacher UCs: Manage personal account information (profile - contact details) | Mỹ Linh | 2025-01-20 | HIGH | COMPLETE
86er952cg | [DOCS] Create Admin UCs: Manage user accounts | Mỹ Linh | 2025-01-18 | URGENT | COMPLETE
86er957y6 | [DOCS] Create Leaner UCs: View enrolled courses | Mạnh Hùng | 2025-01-21 | HIGH | COMPLETE
86er9f9wy | [FE] Install packages | Trọng Nghĩa | 2025-01-16 | URGENT | COMPLETE
86er9qe11 | [DOCS] Draw system models for SRS | Quốc Chương | 2025-01-19 | NORMAL | COMPLETE
86er9q52q | [FE] Implement Homepage UI for Learner | Trọng Nghĩa | 2025-01-19 | HIGH | COMPLETE
86er952nr | [DOCS] Create Learner UCs: View and Edit personal account details | Thị Thúy | 2025-01-20 | HIGH | COMPLETE
86er8ek9x | [DOCS] Phase 1 | Trọng Nghĩa - Mạnh Hùng - Mỹ Linh - Thị Thúy | 2025-01-20 12:00 | URGENT | COMPLETE
86er954vn | [DOCS] Create Teacher UCs: Create and Manage Quizzes. | Mạnh Hùng | 2025-01-24 | HIGH | COMPLETE
86er9558y | [DOCS] Create Admin UCs: Send notifications or announcements to users | Mạnh Hùng | 2025-01-27 | HIGH | COMPLETE
86er951wv | [DOCS] Create Teacher UCs: Create - Edit and Delete new courses with multimedia content. | Trọng Nghĩa | 2025-01-21 | URGENT | COMPLETE
86er954rp | [DOCS] Create Teacher UCs: Dashboard (List registered learner and created course) | Thị Thúy | 2025-01-24 | HIGH | COMPLETE
86er955cg | [DOCS] Create Admin UCs: Approve or reject actions of the teacher of course (create - update - delete,....) | Mỹ Linh | 2025-01-24 | HIGH | COMPLETE
86er8mfg2 | [DOCS] Create Learner UCs: Enroll in courses | Trọng Nghĩa | 2025-01-24 | HIGH | COMPLETE
86er952zx | [DOCS] Phase 2 | Trọng Nghĩa - Mạnh Hùng - Mỹ Linh - Thị Thúy | 2025-01-24 12:00 | HIGH | COMPLETE
86er952md | [DOCS] Create Learner UCs: Track progress for each enrolled course | Trọng Nghĩa | 2025-01-26 | HIGH | COMPLETE
86er9541t | [DOCS] Create Teacher UCs: View revenue reports for their courses | Mỹ Linh | 2025-01-26 | HIGH | COMPLETE
86er9551g | [DOCS] Create Admin UCs: View - edit and analyze reports on users - courses - and payments | Thị Thúy | 2025-01-26 | HIGH | COMPLETE
86er95322 | [DOCS] Phase 3 | Trọng Nghĩa - Mạnh Hùng - Mỹ Linh - Thị Thúy | 2025-01-26 12:00 | HIGH | COMPLETE
86er95363 | [DOCS] Phase 4 | Mạnh Hùng | 2025-01-28 12:00 | HIGH | COMPLETE
86er88yve | [DOCS] Use Case Design | Trọng Nghĩa - Mạnh Hùng - Mỹ Linh - Thị Thúy | 2025-01-28 | URGENT | COMPLETE
86era86up | [FE] Implement UI for Teacher Dashboard | Quốc Chương | 2025-01-23 | HIGH | COMPLETE
86er8xb7q | [FE] Implement feature login/register UCs | Quốc Chương | 2025-02-07 | HIGH | COMPLETE
86era870a | [FE] Implement UI for Become a Teacher | Mỹ Linh | 2025-01-23 | HIGH | COMPLETE
86erbtcgy | [FE] Implement UI for Learner Checkout | Mỹ Linh | 2025-02-09 | NORMAL | COMPLETE
86era86vh | [FE] Implement UI for Teacher Setting | Trọng Nghĩa | 2025-01-23 | HIGH | COMPLETE
86erbtcv2 | [FE] Implement UI for Homepage | Trọng Nghĩa | 2025-02-09 | NORMAL | COMPLETE
86era86re | [FE] Implement UI for Student Setting | Mạnh Hùng | 2025-01-23 | HIGH | COMPLETE
86era86gm | [FE] Implement UI for Student Dashboard | Thị Thúy | 2025-01-23 | HIGH | COMPLETE
86erbtd3j | [FE] Implement UI for Teacher Profile | Thị Thúy | 2025-02-09 | NORMAL | COMPLETE
86erbtcnv | [FE] Implement UI for Watch Course | Mỹ Linh | 2025-02-13 | NORMAL | COMPLETE
86erbtdaz | [FE] Implement UI for page 404 | Quốc Chương | 2025-02-16 | HIGH | COMPLETE
86erbtcwp | [FE] Implement UI for Learner Course | Trọng Nghĩa | 2025-02-16 | HIGH | COMPLETE
86erhj319 | [BE] implement CRUD for Courses API | Quốc Chương | 2025-02-16 | URGENT | COMPLETE
86erht6mb | [BE] Implement CRUD for Section API in each Course | Quốc Chương | 2025-02-16 | URGENT | COMPLETE
86erht6ng | [BE] Implement CRUD for Lecture API in each Section | Quốc Chương | 2025-02-18 | HIGH | COMPLETE
86erbtd1x | [FE] Implement UI for Teacher my courses | Mỹ Linh - Trọng Nghĩa | 2025-02-16 | HIGH | COMPLETE
86erbtd84 | [FE] Implement UI for Contact | Thị Thúy | 2025-02-16 | NORMAL | COMPLETE
86erg48jh | [FE] Implement UI for FAQ | Thị Thúy | 2025-02-16 | NORMAL | COMPLETE
86erkk2cp | [BE] Implement API Payment Course | Quốc Chương | 2025-02-26 | URGENT | COMPLETE
86erj1d37 | [FE] Implement UI for Teacher Create Course | Trọng Nghĩa | 2025-02-23 | HIGH | COMPLETE
86erj1daa | [FE] Implement UI for Learner_Wishlist | Thị Thúy | 2025-02-23 | NORMAL | COMPLETE
86erj1dc0 | [FE] Implement UI for Learner_Purchase_History | Thị Thúy | 2025-02-23 | NORMAL | COMPLETE
86erj1ddj | [FE] Implement UI for About | Thị Thúy | 2025-03-02 | LOW | COMPLETE
86ermyrk1 | [BE] Implement API for Become A Teacher | Quốc Chương | 2025-03-01 | URGENT | COMPLETE
86ermpt1b | [BE] Implement API for Learning Course | Quốc Chương | 2025-02-23 | URGENT | COMPLETE
86erj1cyx | [FE] Implement UI for Course_List & Course_List_Filter | Mỹ Linh | 2025-03-02 | HIGH | COMPLETE
86erj1d7r | [FE] Implement UI for Home page integration API (list course) | Mạnh Hùng | 2025-02-23 | HIGH | COMPLETE
86erbtcag | [FE] Implement UI for Course Detail | Mạnh Hùng | 2025-02-23 | URGENT | COMPLETE
86erj1dh0 | [FE] Implement UI for Career | Thị Thúy | 2025-03-02 | LOW | COMPLETE
86erj1dj3 | [FE] Implement UI for Career_Detail | Thị Thúy | 2025-03-02 | LOW | COMPLETE
86erk560a | [FE] Implement UI for Admin Login | Minh Vương | 2025-02-23 | URGENT | COMPLETE
86ermr31g | [FE] Integrate API Progress for UI Watch Course | Trọng Nghĩa | 2025-03-01 | URGENT | COMPLETE
86ernx8a4 | [FE] Integrate API get list courses created by teacher | Trọng Nghĩa | 2025-03-02 | HIGH | COMPLETE
86erpd7gx | [BE] Implement API for Realtime Chat | Quốc Chương | 2025-03-10 | URGENT | COMPLETE
86ermtqt9 | [FE] Integrate API List Courses for UI Learner Dashboard & Learner Courses | Mạnh Hùng | 2025-03-04 | URGENT | COMPLETE
86erj1d9f | [FE] Implement UI for Teacher_Earning & Teacher_Earning_New_Payment_Card | Quốc Chương - Thị Thúy | 2025-03-02 | HIGH | COMPLETE
86erj1dp4 | [FE] Implement UI for Course detail integration API (get course) | Mạnh Hùng | 2025-03-03 | HIGH | COMPLETE
86erpky2j | [TESTING] Teacher - Teacher_Profile Page | Minh Vương | 2025-02-23 | HIGH | COMPLETE
86erpm2yw | [FE] Implement UI for Learner Message | Thị Thúy | 2025-03-07 | URGENT | COMPLETE
86erpm2yz | [FE] Implement UI for Teacher Message | Thị Thúy | 2025-03-09 | HIGH | COMPLETE
86ernx8tp | [FE] Integrate API update course and lecture for teacher | Trọng Nghĩa | 2025-03-09 | HIGH | COMPLETE
86ernyn3w | [FE] Implement UI for Admin Dashboard | Mỹ Linh | 2025-03-09 | HIGH | COMPLETE
86erqkvma | [FE] Integrate API for Login Admin | Mỹ Linh | 2025-03-07 | URGENT | COMPLETE
86era86a0 | [FE] Implement UI | Mỹ Linh - Thị Thúy - Mạnh Hùng - Trọng Nghĩa - Quốc Chương | 2025-03-20 | HIGH | COMPLETE
86er88ywx | [DOCS] API Design | Quốc Chương - Minh Vương | 2025-03-20 | HIGH | COMPLETE
86erpefqf | [TESTING] System Testing | Thị Thúy - Mỹ Linh | 2025-03-20 | HIGH | COMPLETE
86erpkwwq | [TESTING] Teacher Features Testing | Mỹ Linh | 2025-03-23 | HIGH | COMPLETE
86erpkxrh | [TESTING] Learner - Home Page | Thị Thúy | 2025-03-23 | HIGH | COMPLETE
86erpkxy1 | [TESTING] Learner - Category Page | Thị Thúy | 2025-03-23 | HIGH | COMPLETE
86erpkxzf | [TESTING] Learner - Course_List Page | Thị Thúy | 2025-03-23 | HIGH | COMPLETE
86erqcd6d | [TESTING] Learner - Course_Detail Page | Thị Thúy | 2025-03-23 | HIGH | COMPLETE
86erqcew8 | [TESTING] Learner - Dashboard Page | Thị Thúy | 2025-03-23 | HIGH | COMPLETE
86erqemcb | [TESTING] Learner - Courses Page | Mỹ Linh | 2025-03-23 | HIGH | COMPLETE
86erqf18p | [TESTING] Learner - Wishlist Page | Mỹ Linh | 2025-03-23 | HIGH | COMPLETE
86erqf2wb | [TESTING] Learner - Purchase History Page | Mỹ Linh | 2025-03-23 | HIGH | COMPLETE
86erqf4nk | [TESTING] Learner - Setting Page | Mỹ Linh | 2025-03-23 | HIGH | COMPLETE
86erpkwt2 | [TESTING] Learner Features Testing | Mỹ Linh | 2025-03-23 | HIGH | COMPLETE
86erqkex6 | [FE] Implement UI & Integrate API for Category | Mạnh Hùng | 2025-03-12 | HIGH | COMPLETE
86erqhp93 | [FE] Implement API for all tab in Learner Profile | Mỹ Linh | 2025-03-11 | URGENT | COMPLETE
86erqd1n5 | [TESTING] Learner - Watch_Course Page | Thị Thúy | 2025-03-23 | HIGH | COMPLETE
86erbtcz0 | [FE] Implement UI for Teacher my course detail | Mỹ Linh | 2025-03-19 | HIGH | COMPLETE
86ernym3u | [FE] Implement UI & Integrate API for handle salary of teacher for admin | Trọng Nghĩa | 2025-03-12 | HIGH | COMPLETE
86erpkwy6 | [TESTING] Admin Features Testing | Thị Thúy | 2025-03-16 | HIGH | COMPLETE
86erpky67 | [TESTING] Teacher - Become_A_Teacher Page | Thị Thúy | 2025-03-16 | HIGH | COMPLETE
86erpky6z | [TESTING] Teacher - Teacher_Dashboard Page | Mỹ Linh | 2025-03-16 | HIGH | COMPLETE
86erpkyfu | [TESTING] Learner - Learner_Message Page | Mỹ Linh | 2025-03-16 | HIGH | COMPLETE
86erqkgyx | [FE] Integrate API for Learner Message | Minh Vương | 2025-03-16 | HIGH | COMPLETE
86erqkh23 | [FE] Integrate API for Teacher Message | Minh Vương | 2025-03-16 | HIGH | COMPLETE
86erq00uh | [BE] Implement API handle salary for teacher | Quốc Chương | 2025-03-10 | URGENT | COMPLETE
86ernyhu3 | [FE] Implement UI & Integrate API check courses for admin | Mạnh Hùng | 2025-03-12 | URGENT | COMPLETE
CLOSE
Task ID | Task Name | Assignee | Due Date | Priority | Status
86erqd1av | [TESTING] Learner - Gift_Course Page | Mỹ Linh |  | LOW | CLOSE
IN REVIEW
Task ID | Task Name | Assignee | Due Date | Priority | Status
IN PROGRESS
Task ID | Task Name | Assignee | Due Date | Priority | Status
TO DO
Task ID | Task Name | Assignee | Due Date | Priority | Status
🐞Bugs / Issues
CLOSE
Task ID | Task Name | Assignee | Due Date | Priority | Status
86erqbbzk | Learner - Purchase history | Mạnh Hùng | 2025-03-12 | HIGH | COMPLETE
IN REVIEW
Task ID | Task Name | Assignee | Due Date | Priority | Status
OPEN
Task ID | Task Name | Assignee | Due Date | Priority | Status
RESOLVED
Task ID | Task Name | Assignee | Due Date | Priority | Status
86erq2j2g | Learner - Home Page | Trọng Nghĩa - Quốc Chương | 2025-03-04 19:00 | URGENT | COMPLETE
86erq2xut | Learner - Category Page | Minh Vương | 2025-03-04 19:00 | URGENT | COMPLETE
86erq2xeu | Teacher - Create lecture | Quốc Chương | 2025-03-04 19:00 | URGENT | COMPLETE
86erqc8q5 | Learner - Course-list Page | Quốc Chương | 2025-03-04 19:00 | URGENT | COMPLETE
86erqcdfc | Learner - Course-detail Page | Trọng Nghĩa | 2025-03-04 19:00 | URGENT | COMPLETE
86erqeh9f | Learner - Dashboard Page | Minh Vương | 2025-03-16 | URGENT | COMPLETE
86erqenye | Learner - Course Page | Quốc Chương | 2025-03-16 | HIGH | COMPLETE
86erqf1e5 | Learner - Wishlist Page | Minh Vương | 2025-03-16 | LOW | COMPLETE
86erqf4qt | Learner - Setting Page | Trọng Nghĩa | 2025-03-16 | LOW | COMPLETE
86ertenh4 | Learner - Watch_course Page | Minh Vương | 2025-03-16 | URGENT | COMPLETE
86erq2nqr | Teacher - My Courses | Quốc Chương | 2025-03-04 19:00 | URGENT | COMPLETE
86erq2p4h | Teacher - Course detail | Quốc Chương | 2025-03-04 19:00 | URGENT | COMPLETE
86erqbdhk | Teacher - Profile | Quốc Chương | 2025-03-16 | LOW | COMPLETE
86erq2pv7 | Teacher - Edit course | Trọng Nghĩa | 2025-03-04 19:00 | URGENT | COMPLETE
86erq2y8a | Teacher - Edit lecture | Trọng Nghĩa | 2025-03-04 19:00 | URGENT | COMPLETE

## Pull Request Frontend
PR No. | Title | State | Created By | Created Date | Updated Date | Closed Date | URL
217 | update: release v1.4.3 | closed | htnghia1423 | 2025-03-26 03:40 | 2025-03-26 03:41 | 2025-03-26 03:41 | https://github.com/lzaycoe/brainbox-frontend/pull/217
216 | fix error in build | closed | htnghia1423 | 2025-03-26 03:37 | 2025-03-26 03:39 | 2025-03-26 03:39 | https://github.com/lzaycoe/brainbox-frontend/pull/216
215 | update: release version 1.4.2 | closed | htnghia1423 | 2025-03-26 03:20 | 2025-03-26 03:23 | 2025-03-26 03:23 | https://github.com/lzaycoe/brainbox-frontend/pull/215
214 | update project version | closed | htnghia1423 | 2025-03-26 03:18 | 2025-03-26 03:19 | 2025-03-26 03:19 | https://github.com/lzaycoe/brainbox-frontend/pull/214
213 | Hotfix/fix all bugs | closed | htnghia1423 | 2025-03-26 01:17 | 2025-03-26 03:16 | 2025-03-26 03:16 | https://github.com/lzaycoe/brainbox-frontend/pull/213
212 | update: release version 1.4.1 | closed | bakaqc | 2025-03-25 14:09 | 2025-03-25 14:16 | 2025-03-25 14:16 | https://github.com/lzaycoe/brainbox-frontend/pull/212
211 | Hotfix/fix all bugs chuong | closed | bakaqc | 2025-03-25 14:08 | 2025-03-25 14:10 | 2025-03-25 14:10 | https://github.com/lzaycoe/brainbox-frontend/pull/211
210 | Hotfix/fix all bugs hung | closed | punhe | 2025-03-24 09:34 | 2025-03-25 14:47 | 2025-03-25 14:06 | https://github.com/lzaycoe/brainbox-frontend/pull/210
209 | hotfix: error deployment | closed | bakaqc | 2025-03-23 14:14 | 2025-03-23 14:15 | 2025-03-23 14:15 | https://github.com/lzaycoe/brainbox-frontend/pull/209
208 | hotfix: error deployment | closed | bakaqc | 2025-03-23 14:12 | 2025-03-23 14:13 | 2025-03-23 14:13 | https://github.com/lzaycoe/brainbox-frontend/pull/208
207 | update: merge code from main | closed | bakaqc | 2025-03-23 13:53 | 2025-03-23 13:54 | 2025-03-23 13:54 | https://github.com/lzaycoe/brainbox-frontend/pull/207
206 | dev: release version 1.4.0 | closed | bakaqc | 2025-03-23 10:10 | 2025-03-23 13:47 | 2025-03-23 13:47 | https://github.com/lzaycoe/brainbox-frontend/pull/206
205 | [FE] Integrate API for Message | closed | bakaqc | 2025-03-23 10:07 | 2025-03-23 13:43 | 2025-03-23 13:43 | https://github.com/lzaycoe/brainbox-frontend/pull/205
204 | [FE] Implement UI & Integrate API check courses for admin | closed | punhe | 2025-03-22 14:33 | 2025-03-22 14:39 | 2025-03-22 14:38 | https://github.com/lzaycoe/brainbox-frontend/pull/204
203 | [FE] Implement UI & Integrate API check courses for admin | closed | punhe | 2025-03-22 14:06 | 2025-03-22 14:39 | 2025-03-22 14:32 | https://github.com/lzaycoe/brainbox-frontend/pull/203
202 | update: merge code from dev | closed | bakaqc | 2025-03-22 09:07 | 2025-03-22 09:18 | 2025-03-22 09:18 | https://github.com/lzaycoe/brainbox-frontend/pull/202
201 | [FE] Integrate API for Realtime Chat | closed | bakaqc | 2025-03-22 08:19 | 2025-03-23 13:52 | 2025-03-23 10:06 | https://github.com/lzaycoe/brainbox-frontend/pull/201
200 | [FE] Implement UI & Integrate API for handle salary of teacher for admin | closed | htnghia1423 | 2025-03-21 14:51 | 2025-03-21 15:31 | 2025-03-21 15:31 | https://github.com/lzaycoe/brainbox-frontend/pull/200
199 | Dev | closed | htnghia1423 | 2025-03-20 09:04 | 2025-03-20 09:06 | 2025-03-20 09:06 | https://github.com/lzaycoe/brainbox-frontend/pull/199
198 | Feature/task 189 | closed | linhlm0210 | 2025-03-19 14:40 | 2025-03-20 02:44 | 2025-03-20 02:43 | https://github.com/lzaycoe/brainbox-frontend/pull/198
197 | [FE] Implement UI & Integrate API for Category | closed | punhe | 2025-03-19 03:25 | 2025-03-21 03:18 | 2025-03-19 07:26 | https://github.com/lzaycoe/brainbox-frontend/pull/197
196 | Feature/task 167 | closed | linhlm0210 | 2025-03-19 03:25 | 2025-03-19 03:49 | 2025-03-19 03:48 | https://github.com/lzaycoe/brainbox-frontend/pull/196
195 | [FE] Implement UI & Integrate API check courses for admin | closed | punhe | 2025-03-16 18:01 | 2025-03-22 14:06 | 2025-03-22 14:06 | https://github.com/lzaycoe/brainbox-frontend/pull/195
194 | [FE] Implement UI & Integrate API for handle salary of teacher for admin | closed | htnghia1423 | 2025-03-16 12:49 | 2025-03-21 15:31 | 2025-03-21 14:47 | https://github.com/lzaycoe/brainbox-frontend/pull/194
193 | [FE] Implement UI & Integrate API for Category | closed | punhe | 2025-03-16 11:14 | 2025-03-21 03:17 | 2025-03-19 03:24 | https://github.com/lzaycoe/brainbox-frontend/pull/193
192 | [FE] Implement UI for Teacher my course detail | closed | linhlm0210 | 2025-03-15 15:47 | 2025-03-19 13:58 | 2025-03-19 13:58 | https://github.com/lzaycoe/brainbox-frontend/pull/192
188 | Feature/task 167 linh | closed | linhlm0210 | 2025-03-15 01:26 | 2025-03-20 03:52 | 2025-03-19 03:24 | https://github.com/lzaycoe/brainbox-frontend/pull/188
186 | Hotfix/fix all bugs | closed | htnghia1423 | 2025-03-14 01:57 | 2025-03-14 03:52 | 2025-03-14 02:08 | https://github.com/lzaycoe/brainbox-frontend/pull/186
185 | Hotfix/fix all bugs nghia | closed | htnghia1423 | 2025-03-14 01:56 | 2025-03-23 13:52 | 2025-03-14 01:57 | https://github.com/lzaycoe/brainbox-frontend/pull/185
184 | fix: increase video height in CourseVideo component | closed | bakaqc | 2025-03-14 01:39 | 2025-03-14 01:53 | 2025-03-14 01:40 | https://github.com/lzaycoe/brainbox-frontend/pull/184
183 | dev: release production v1.3.2 | closed | bakaqc | 2025-03-14 01:21 | 2025-03-14 01:53 | 2025-03-14 01:43 | https://github.com/lzaycoe/brainbox-frontend/pull/183
182 | dev: merge code from main | closed | bakaqc | 2025-03-14 01:20 | 2025-03-14 03:47 | 2025-03-14 03:47 | https://github.com/lzaycoe/brainbox-frontend/pull/182
181 | Dev | closed | htnghia1423 | 2025-03-14 01:12 | 2025-03-14 01:12 | 2025-03-14 01:12 | https://github.com/lzaycoe/brainbox-frontend/pull/181
180 | add: admin path | closed | linhlm0210 | 2025-03-13 15:59 | 2025-03-14 01:20 | 2025-03-14 01:20 | https://github.com/lzaycoe/brainbox-frontend/pull/180
179 | Hotfix/fix all bugs | closed | htnghia1423 | 2025-03-13 14:50 | 2025-03-13 14:53 | 2025-03-13 14:53 | https://github.com/lzaycoe/brainbox-frontend/pull/179
178 | fix: add pattern for display image | closed | htnghia1423 | 2025-03-13 14:48 | 2025-03-13 14:49 | 2025-03-13 14:49 | https://github.com/lzaycoe/brainbox-frontend/pull/178
177 | dev: release production v1.3.1 | closed | htnghia1423 | 2025-03-13 14:36 | 2025-03-13 14:39 | 2025-03-13 14:39 | https://github.com/lzaycoe/brainbox-frontend/pull/177
176 | Hotfix/fix all bugs | closed | htnghia1423 | 2025-03-13 14:34 | 2025-03-13 14:35 | 2025-03-13 14:35 | https://github.com/lzaycoe/brainbox-frontend/pull/176
175 | fix: remove unuse import | closed | htnghia1423 | 2025-03-13 14:32 | 2025-03-13 14:34 | 2025-03-13 14:34 | https://github.com/lzaycoe/brainbox-frontend/pull/175
174 | dev: release production v1.3.0 | closed | bakaqc | 2025-03-13 14:17 | 2025-03-13 14:19 | 2025-03-13 14:19 | https://github.com/lzaycoe/brainbox-frontend/pull/174
173 | fix display paid course for learner | closed | htnghia1423 | 2025-03-13 13:21 | 2025-03-13 14:32 | 2025-03-13 13:23 | https://github.com/lzaycoe/brainbox-frontend/pull/173
172 | [FE] Implement UI & Integrate API check courses for admin | closed | punhe | 2025-03-13 13:15 | 2025-03-13 13:46 | 2025-03-13 13:46 | https://github.com/lzaycoe/brainbox-frontend/pull/172
170 | fix: display paid courses for learner | closed | htnghia1423 | 2025-03-13 09:45 | 2025-03-13 13:19 | 2025-03-13 13:19 | https://github.com/lzaycoe/brainbox-frontend/pull/170
169 | Dev | closed | htnghia1423 | 2025-03-12 03:34 | 2025-03-12 03:35 | 2025-03-12 03:35 | https://github.com/lzaycoe/brainbox-frontend/pull/169
168 | Intergrate check course for Admin | closed | punhe | 2025-03-11 00:46 | 2025-03-13 13:47 | 2025-03-13 13:47 | https://github.com/lzaycoe/brainbox-frontend/pull/168
166 | admin: login + dashboard + fix payment | closed | linhlm0210 | 2025-03-11 00:34 | 2025-03-11 00:49 | 2025-03-11 00:42 | https://github.com/lzaycoe/brainbox-frontend/pull/166
165 | [FE] Integrate API update course and lecture for teacher | closed | htnghia1423 | 2025-03-10 14:17 | 2025-03-10 14:25 | 2025-03-10 14:24 | https://github.com/lzaycoe/brainbox-frontend/pull/165
164 | Feature/task 157 | closed | yuhtnguyen | 2025-03-10 13:36 | 2025-03-13 14:33 | 2025-03-10 13:40 | https://github.com/lzaycoe/brainbox-frontend/pull/164
163 | Feature/task 154 | closed | yuhtnguyen | 2025-03-10 13:35 | 2025-03-13 14:33 | 2025-03-10 13:37 | https://github.com/lzaycoe/brainbox-frontend/pull/163
162 | [FE] Integrate API update course and lecture for teacher | closed | htnghia1423 | 2025-03-10 03:06 | 2025-03-10 14:25 | 2025-03-10 14:16 | https://github.com/lzaycoe/brainbox-frontend/pull/162
161 | [FE] Implement UI & Integrate API check courses for admin | closed | punhe | 2025-03-07 12:15 | 2025-03-11 00:45 | 2025-03-11 00:45 | https://github.com/lzaycoe/brainbox-frontend/pull/161
160 | Feature/task 157_ Message for teacher | closed | yuhtnguyen | 2025-03-07 04:38 | 2025-03-13 14:33 | 2025-03-10 13:35 | https://github.com/lzaycoe/brainbox-frontend/pull/160
159 | dev: merge code from main | closed | bakaqc | 2025-03-07 03:59 | 2025-03-13 13:58 | 2025-03-13 13:58 | https://github.com/lzaycoe/brainbox-frontend/pull/159
158 | Dev | closed | htnghia1423 | 2025-03-07 03:29 | 2025-03-07 03:30 | 2025-03-07 03:29 | https://github.com/lzaycoe/brainbox-frontend/pull/158
155 | add: implement UI message learner | closed | yuhtnguyen | 2025-03-06 11:07 | 2025-03-13 14:33 | 2025-03-10 13:35 | https://github.com/lzaycoe/brainbox-frontend/pull/155
153 | admin: login + dashboard + fix payment | closed | linhlm0210 | 2025-03-05 04:27 | 2025-03-11 00:45 | 2025-03-11 00:34 | https://github.com/lzaycoe/brainbox-frontend/pull/153
151 | dev: release production v1.2.1 | closed | bakaqc | 2025-03-04 15:13 | 2025-03-04 15:18 | 2025-03-04 15:18 | https://github.com/lzaycoe/brainbox-frontend/pull/151
150 | update: package version | closed | htnghia1423 | 2025-03-04 15:11 | 2025-03-07 03:04 | 2025-03-04 15:11 | https://github.com/lzaycoe/brainbox-frontend/pull/150
149 | Hotfix/fix all bugs | closed | htnghia1423 | 2025-03-04 15:09 | 2025-03-04 15:12 | 2025-03-04 15:12 | https://github.com/lzaycoe/brainbox-frontend/pull/149
148 | fix: fix error build | closed | htnghia1423 | 2025-03-04 15:08 | 2025-03-04 15:08 | 2025-03-04 15:08 | https://github.com/lzaycoe/brainbox-frontend/pull/148
147 | Hotfix/fix all bugs | closed | bakaqc | 2025-03-04 14:56 | 2025-03-04 14:58 | 2025-03-04 14:58 | https://github.com/lzaycoe/brainbox-frontend/pull/147
146 | Hotfix/fix all bugs chuong2 | closed | bakaqc | 2025-03-04 14:14 | 2025-03-04 15:03 | 2025-03-04 14:16 | https://github.com/lzaycoe/brainbox-frontend/pull/146
145 | dev: release production v1.2.0 | closed | bakaqc | 2025-03-04 14:00 | 2025-03-04 14:59 | 2025-03-04 14:59 | https://github.com/lzaycoe/brainbox-frontend/pull/145
144 | Attach link | closed | punhe | 2025-03-04 11:07 | 2025-03-04 15:03 | 2025-03-04 14:40 | https://github.com/lzaycoe/brainbox-frontend/pull/144
143 | Hotfix all bugs | closed | htnghia1423 | 2025-03-04 07:05 | 2025-03-04 14:55 | 2025-03-04 14:55 | https://github.com/lzaycoe/brainbox-frontend/pull/143
142 | Feature/task 127 | closed | htnghia1423 | 2025-03-04 00:21 | 2025-03-04 00:22 | 2025-03-04 00:22 | https://github.com/lzaycoe/brainbox-frontend/pull/142
141 | dev: merge code from dev | closed | bakaqc | 2025-03-03 15:43 | 2025-03-04 00:19 | 2025-03-04 00:19 | https://github.com/lzaycoe/brainbox-frontend/pull/141
140 | [FE] Integrate API update course and lecture for teacher | closed | htnghia1423 | 2025-03-03 15:35 | 2025-03-03 15:42 | 2025-03-03 15:42 | https://github.com/lzaycoe/brainbox-frontend/pull/140
139 | [FE] Integrate API update course and lecture for teacher | closed | htnghia1423 | 2025-03-03 15:01 | 2025-03-03 15:34 | 2025-03-03 15:34 | https://github.com/lzaycoe/brainbox-frontend/pull/139
138 | Feature/task 111 | closed | linhlm0210 | 2025-03-03 14:50 | 2025-03-03 15:00 | 2025-03-03 14:59 | https://github.com/lzaycoe/brainbox-frontend/pull/138
137 | fix: fix sonar scan | closed | punhe | 2025-03-03 14:18 | 2025-03-03 15:02 | 2025-03-03 14:19 | https://github.com/lzaycoe/brainbox-frontend/pull/137
136 | fix: fix lint build | closed | punhe | 2025-03-03 14:10 | 2025-03-03 14:11 | 2025-03-03 14:11 | https://github.com/lzaycoe/brainbox-frontend/pull/136
135 | Feature/task 101 | closed | punhe | 2025-03-03 13:50 | 2025-03-03 14:23 | 2025-03-03 14:21 | https://github.com/lzaycoe/brainbox-frontend/pull/135
134 | Feature/task 79 | closed | yuhtnguyen | 2025-03-03 13:32 | 2025-03-03 15:02 | 2025-03-03 13:34 | https://github.com/lzaycoe/brainbox-frontend/pull/134
133 | fix: fix import alias | closed | punhe | 2025-03-03 13:11 | 2025-03-03 13:13 | 2025-03-03 13:12 | https://github.com/lzaycoe/brainbox-frontend/pull/133
132 | Feature/task 116 | closed | punhe | 2025-03-03 13:07 | 2025-03-03 13:13 | 2025-03-03 13:13 | https://github.com/lzaycoe/brainbox-frontend/pull/132
131 | [FE] Integrate API List Courses for UI Learner Dashboard & Learner Courses | closed | punhe | 2025-03-03 12:40 | 2025-03-03 13:06 | 2025-03-03 13:06 | https://github.com/lzaycoe/brainbox-frontend/pull/131
130 | Feature/task 111 linh | closed | linhlm0210 | 2025-03-03 09:40 | 2025-03-03 15:00 | 2025-03-03 14:49 | https://github.com/lzaycoe/brainbox-frontend/pull/130
129 | [FE] Implement UI for Course detail integration API (get course) | closed | punhe | 2025-03-03 06:08 | 2025-03-03 13:59 | 2025-03-03 13:50 | https://github.com/lzaycoe/brainbox-frontend/pull/129
128 | Feature/fix bug | closed | bakaqc | 2025-03-03 03:44 | 2025-03-03 15:03 | 2025-03-03 13:33 | https://github.com/lzaycoe/brainbox-frontend/pull/128
126 | fix error display in course list learner | closed | htnghia1423 | 2025-03-03 02:07 | 2025-03-03 03:43 | 2025-03-03 03:43 | https://github.com/lzaycoe/brainbox-frontend/pull/126
125 | Integrate API Progress for UI Watch Course | closed | htnghia1423 | 2025-03-02 08:32 | 2025-03-02 08:44 | 2025-03-02 08:44 | https://github.com/lzaycoe/brainbox-frontend/pull/125
124 | [FE] Integrate API Progress for UI Watch Course | closed | htnghia1423 | 2025-03-02 08:30 | 2025-03-02 08:32 | 2025-03-02 08:31 | https://github.com/lzaycoe/brainbox-frontend/pull/124
123 | Integrate API Progress for UI Watch Course | closed | htnghia1423 | 2025-03-02 04:24 | 2025-03-02 08:32 | 2025-03-02 08:29 | https://github.com/lzaycoe/brainbox-frontend/pull/123
122 | Feature/task 79 thuy | closed | yuhtnguyen | 2025-03-01 11:06 | 2025-03-03 15:02 | 2025-03-03 13:31 | https://github.com/lzaycoe/brainbox-frontend/pull/122
121 | add: add UI earning for teacher | closed | yuhtnguyen | 2025-03-01 05:45 | 2025-03-01 10:13 | 2025-03-01 10:13 | https://github.com/lzaycoe/brainbox-frontend/pull/121
119 | Feature/task 96 | closed | yuhtnguyen | 2025-02-28 04:04 | 2025-02-28 04:22 | 2025-02-28 04:06 | https://github.com/lzaycoe/brainbox-frontend/pull/119
118 | Feature/task 97 | closed | yuhtnguyen | 2025-02-28 03:53 | 2025-02-28 04:22 | 2025-02-28 04:02 | https://github.com/lzaycoe/brainbox-frontend/pull/118
117 | [FE] Implement UI for Home page integration API (list course) | closed | punhe | 2025-02-28 03:52 | 2025-02-28 03:54 | 2025-02-28 03:54 | https://github.com/lzaycoe/brainbox-frontend/pull/117
115 | [FE] Implement UI for Home page integration API (list course) | closed | punhe | 2025-02-28 03:33 | 2025-02-28 03:57 | 2025-02-28 03:57 | https://github.com/lzaycoe/brainbox-frontend/pull/115
114 | Feature/task 101 hung | closed | punhe | 2025-02-28 03:27 | 2025-02-28 03:32 | 2025-02-28 03:32 | https://github.com/lzaycoe/brainbox-frontend/pull/114
113 | Feature/task 90 | closed | linhlm0210 | 2025-02-27 04:08 | 2025-02-27 13:56 | 2025-02-27 13:29 | https://github.com/lzaycoe/brainbox-frontend/pull/113
112 | [FE] Implement UI for Course Detail | closed | punhe | 2025-02-26 17:01 | 2025-02-27 08:06 | 2025-02-27 06:48 | https://github.com/lzaycoe/brainbox-frontend/pull/112
110 | [FE] Implement UI for Course_List & Course_List_Filter #90 | closed | linhlm0210 | 2025-02-26 15:52 | 2025-02-27 13:56 | 2025-02-27 04:07 | https://github.com/lzaycoe/brainbox-frontend/pull/110
109 | Feature/task 97 thuy_Career detail | closed | yuhtnguyen | 2025-02-26 12:42 | 2025-02-28 04:22 | 2025-02-28 03:52 | https://github.com/lzaycoe/brainbox-frontend/pull/109
108 | Feature/task 96 thuy_Career | closed | yuhtnguyen | 2025-02-26 04:17 | 2025-02-28 04:22 | 2025-02-28 04:02 | https://github.com/lzaycoe/brainbox-frontend/pull/108
107 | Feature/task 95 | closed | yuhtnguyen | 2025-02-26 04:05 | 2025-02-28 04:22 | 2025-02-26 04:06 | https://github.com/lzaycoe/brainbox-frontend/pull/107
105 | [FE] Implement UI for Teacher Create Course | closed | htnghia1423 | 2025-02-26 03:46 | 2025-02-26 03:54 | 2025-02-26 03:52 | https://github.com/lzaycoe/brainbox-frontend/pull/105
104 | Feature/task 81 | closed | yuhtnguyen | 2025-02-26 02:44 | 2025-02-28 04:23 | 2025-02-26 02:48 | https://github.com/lzaycoe/brainbox-frontend/pull/104
103 | Feature/task 80 | closed | yuhtnguyen | 2025-02-26 02:07 | 2025-02-26 02:20 | 2025-02-26 02:20 | https://github.com/lzaycoe/brainbox-frontend/pull/103
102 | [FE] Implement UI for Teacher Create Course | closed | htnghia1423 | 2025-02-25 13:05 | 2025-02-26 03:52 | 2025-02-26 03:44 | https://github.com/lzaycoe/brainbox-frontend/pull/102
100 | [FE] Implement UI for Course Detail | closed | punhe | 2025-02-24 17:58 | 2025-02-26 01:44 | 2025-02-26 01:44 | https://github.com/lzaycoe/brainbox-frontend/pull/100
99 | Feature/task 95_about | closed | yuhtnguyen | 2025-02-24 07:03 | 2025-02-28 04:22 | 2025-02-26 04:04 | https://github.com/lzaycoe/brainbox-frontend/pull/99
98 | [FE] Implement UI for Course Detail | closed | punhe | 2025-02-21 16:49 | 2025-03-01 14:05 | 2025-02-27 08:56 | https://github.com/lzaycoe/brainbox-frontend/pull/98
94 | Merge pull request #89 from lzaycoe/feature/task-88_vuong Implement UI for Admin Login page | closed | hardingadonis | 2025-02-20 10:05 | 2025-02-20 11:44 | 2025-02-20 11:44 | https://github.com/lzaycoe/brainbox-frontend/pull/94
93 | Feature/task 81_Purchase History | closed | yuhtnguyen | 2025-02-20 06:20 | 2025-02-28 04:23 | 2025-02-26 02:44 | https://github.com/lzaycoe/brainbox-frontend/pull/93
92 | delete: delete redundant images | closed | yuhtnguyen | 2025-02-20 00:58 | 2025-02-28 04:23 | 2025-02-20 00:59 | https://github.com/lzaycoe/brainbox-frontend/pull/92
91 | Feature/task 57 _ contact | closed | yuhtnguyen | 2025-02-20 00:57 | 2025-02-28 04:23 | 2025-02-20 00:58 | https://github.com/lzaycoe/brainbox-frontend/pull/91
89 | Implement UI for Admin Login page | closed | hardingadonis | 2025-02-19 15:05 | 2025-02-20 10:04 | 2025-02-20 10:04 | https://github.com/lzaycoe/brainbox-frontend/pull/89
87 | [FE] Implement UI for Course Detail | closed | punhe | 2025-02-19 04:04 | 2025-02-21 16:48 | 2025-02-21 16:48 | https://github.com/lzaycoe/brainbox-frontend/pull/87
86 | update: update icon from react | closed | yuhtnguyen | 2025-02-19 01:54 | 2025-02-19 01:56 | 2025-02-19 01:56 | https://github.com/lzaycoe/brainbox-frontend/pull/86
85 | [FE] Implement UI for Learner_Wishlist | closed | yuhtnguyen | 2025-02-18 08:41 | 2025-02-28 04:23 | 2025-02-26 02:06 | https://github.com/lzaycoe/brainbox-frontend/pull/85
84 | Feature/task 72_FAQs | closed | yuhtnguyen | 2025-02-18 07:50 | 2025-02-28 04:23 | 2025-02-20 01:28 | https://github.com/lzaycoe/brainbox-frontend/pull/84
83 | Feature/task 57_contact | closed | yuhtnguyen | 2025-02-18 07:48 | 2025-02-28 04:23 | 2025-02-20 01:28 | https://github.com/lzaycoe/brainbox-frontend/pull/83
78 | [FE] Implement UI for Teacher my courses | closed | htnghia1423 | 2025-02-16 12:41 | 2025-02-26 03:55 | 2025-02-16 12:42 | https://github.com/lzaycoe/brainbox-frontend/pull/78
77 | update: remove use client | closed | htnghia1423 | 2025-02-16 12:40 | 2025-02-16 12:40 | 2025-02-16 12:40 | https://github.com/lzaycoe/brainbox-frontend/pull/77
76 | [FE] Implement UI for Teacher my course detail | closed | htnghia1423 | 2025-02-16 10:51 | 2025-02-16 12:36 | 2025-02-16 12:36 | https://github.com/lzaycoe/brainbox-frontend/pull/76
75 | implement UI for FAQs | closed | yuhtnguyen | 2025-02-16 10:35 | 2025-02-18 07:44 | 2025-02-18 07:44 | https://github.com/lzaycoe/brainbox-frontend/pull/75
74 | [FE] Implement UI for Teacher my courses | closed | linhlm0210 | 2025-02-16 07:30 | 2025-02-27 13:56 | 2025-02-17 04:36 | https://github.com/lzaycoe/brainbox-frontend/pull/74
71 | implement UI for contact (leaner) | closed | yuhtnguyen | 2025-02-15 08:37 | 2025-02-18 07:44 | 2025-02-18 07:44 | https://github.com/lzaycoe/brainbox-frontend/pull/71
69 | [FE] Implement UI for Learner Course | closed | htnghia1423 | 2025-02-15 00:32 | 2025-02-15 01:38 | 2025-02-15 01:38 | https://github.com/lzaycoe/brainbox-frontend/pull/69
68 | [FE] Implement UI for Learner Course | closed | htnghia1423 | 2025-02-14 12:26 | 2025-02-15 02:03 | 2025-02-15 00:31 | https://github.com/lzaycoe/brainbox-frontend/pull/68
67 | [FE] Implement UI for page 404 | closed | bakaqc | 2025-02-14 08:25 | 2025-02-16 08:25 | 2025-02-14 12:20 | https://github.com/lzaycoe/brainbox-frontend/pull/67
66 | add: not found page | closed | bakaqc | 2025-02-14 07:16 | 2025-02-14 08:24 | 2025-02-14 08:24 | https://github.com/lzaycoe/brainbox-frontend/pull/66
64 | release: release v1.0.0 | closed | hardingadonis | 2025-02-14 03:54 | 2025-02-14 03:58 | 2025-02-14 03:58 | https://github.com/lzaycoe/brainbox-frontend/pull/64
63 | Refactor code | closed | hardingadonis | 2025-02-14 03:45 | 2025-02-14 03:49 | 2025-02-14 03:49 | https://github.com/lzaycoe/brainbox-frontend/pull/63
62 | Feature/task 47 | closed | hardingadonis | 2025-02-14 03:31 | 2025-02-14 03:33 | 2025-02-14 03:33 | https://github.com/lzaycoe/brainbox-frontend/pull/62
61 | Hotfix/login feature | closed | bakaqc | 2025-02-13 13:58 | 2025-02-14 02:58 | 2025-02-14 02:58 | https://github.com/lzaycoe/brainbox-frontend/pull/61
60 | Hotfix/login feature chuong | closed | bakaqc | 2025-02-13 11:04 | 2025-02-13 13:57 | 2025-02-13 13:57 | https://github.com/lzaycoe/brainbox-frontend/pull/60
59 | Feature/task 47 linh | closed | linhlm0210 | 2025-02-12 12:08 | 2025-02-14 03:26 | 2025-02-14 03:26 | https://github.com/lzaycoe/brainbox-frontend/pull/59
58 | [FE] Implement UI for Watch Course | closed | linhlm0210 | 2025-02-12 02:39 | 2025-02-12 11:53 | 2025-02-12 11:53 | https://github.com/lzaycoe/brainbox-frontend/pull/58
56 | [FE] Implement UI for Teacher Profile | closed | bakaqc | 2025-02-10 07:02 | 2025-02-10 07:17 | 2025-02-10 07:17 | https://github.com/lzaycoe/brainbox-frontend/pull/56
55 | update: update layout | closed | htnghia1423 | 2025-02-10 06:59 | 2025-02-10 07:24 | 2025-02-10 07:01 | https://github.com/lzaycoe/brainbox-frontend/pull/55
54 | Refactor code | closed | hardingadonis | 2025-02-10 06:32 | 2025-02-10 06:42 | 2025-02-10 06:42 | https://github.com/lzaycoe/brainbox-frontend/pull/54
53 | Dev | closed | yuhtnguyen | 2025-02-10 02:14 | 2025-02-10 02:14 | 2025-02-10 02:14 | https://github.com/lzaycoe/brainbox-frontend/pull/53
51 | Feature/task 43 | closed | htnghia1423 | 2025-02-09 13:03 | 2025-02-09 13:05 | 2025-02-09 13:05 | https://github.com/lzaycoe/brainbox-frontend/pull/51
50 | Feature/task 39 | closed | linhlm0210 | 2025-02-09 12:24 | 2025-02-09 12:25 | 2025-02-09 12:25 | https://github.com/lzaycoe/brainbox-frontend/pull/50
49 | Feature/task 19 | closed | linhlm0210 | 2025-02-09 12:20 | 2025-02-09 12:21 | 2025-02-09 12:21 | https://github.com/lzaycoe/brainbox-frontend/pull/49
48 | [FE] Implement UI for Homepage | closed | htnghia1423 | 2025-02-09 12:19 | 2025-02-09 13:02 | 2025-02-09 13:02 | https://github.com/lzaycoe/brainbox-frontend/pull/48
46 | [FE] Implement UI for Learner Checkout | closed | linhlm0210 | 2025-02-08 14:57 | 2025-02-09 13:22 | 2025-02-09 12:23 | https://github.com/lzaycoe/brainbox-frontend/pull/46
45 | [FE] Implement feature login/register UCs | closed | bakaqc | 2025-02-08 02:55 | 2025-02-09 13:22 | 2025-02-08 02:58 | https://github.com/lzaycoe/brainbox-frontend/pull/45
44 | [FE] Implement feature login/register UCs | closed | bakaqc | 2025-02-08 01:57 | 2025-02-08 02:53 | 2025-02-08 02:53 | https://github.com/lzaycoe/brainbox-frontend/pull/44
42 | Feature/task 38 thuy | closed | yuhtnguyen | 2025-02-07 15:21 | 2025-02-10 07:01 | 2025-02-10 07:01 | https://github.com/lzaycoe/brainbox-frontend/pull/42
40 | [FE] Implement UI for Student Setting | closed | punhe | 2025-02-06 07:04 | 2025-02-09 13:24 | 2025-02-09 13:24 | https://github.com/lzaycoe/brainbox-frontend/pull/40
37 | Feature/task 17 | closed | yuhtnguyen | 2025-02-05 04:25 | 2025-02-10 07:25 | 2025-02-10 07:04 | https://github.com/lzaycoe/brainbox-frontend/pull/37
36 | Feature/task 16 hung | closed | yuhtnguyen | 2025-02-05 04:01 | 2025-02-05 04:02 | 2025-02-05 04:02 | https://github.com/lzaycoe/brainbox-frontend/pull/36
35 | add: dashboard ui for teacher | closed | bakaqc | 2025-02-05 03:35 | 2025-02-08 02:14 | 2025-02-08 02:04 | https://github.com/lzaycoe/brainbox-frontend/pull/35
34 | [FE] Implement UI for Become a Teacher | closed | linhlm0210 | 2025-02-05 01:24 | 2025-02-09 13:22 | 2025-02-09 12:20 | https://github.com/lzaycoe/brainbox-frontend/pull/34
33 | [FE] Implement UI for Student Setting | closed | punhe | 2025-02-02 05:23 | 2025-02-09 13:22 | 2025-02-06 07:02 | https://github.com/lzaycoe/brainbox-frontend/pull/33
32 | [FE] Implement UI for Student Dashboard | closed | yuhtnguyen | 2025-01-27 04:41 | 2025-02-09 13:22 | 2025-02-05 04:24 | https://github.com/lzaycoe/brainbox-frontend/pull/32
31 | [FE] Implement UI for Teacher Setting | closed | htnghia1423 | 2025-01-24 12:13 | 2025-02-09 13:22 | 2025-02-09 13:15 | https://github.com/lzaycoe/brainbox-frontend/pull/31
30 | [FE] Implement UI for Teacher Setting | closed | htnghia1423 | 2025-01-24 02:28 | 2025-01-24 12:12 | 2025-01-24 12:11 | https://github.com/lzaycoe/brainbox-frontend/pull/30
28 | add: implement dashboard ui for teacher | closed | bakaqc | 2025-01-23 06:20 | 2025-02-05 03:34 | 2025-02-05 03:34 | https://github.com/lzaycoe/brainbox-frontend/pull/28
27 | Dev | closed | htnghia1423 | 2025-01-22 02:14 | 2025-01-22 02:15 | 2025-01-22 02:15 | https://github.com/lzaycoe/brainbox-frontend/pull/27
26 | Dev | closed | htnghia1423 | 2025-01-22 02:12 | 2025-01-22 02:13 | 2025-01-22 02:13 | https://github.com/lzaycoe/brainbox-frontend/pull/26
24 | add: 1/2 dashboard page for teacher | closed | bakaqc | 2025-01-21 09:42 | 2025-01-22 02:07 | 2025-01-22 02:07 | https://github.com/lzaycoe/brainbox-frontend/pull/24
23 | add: dashboard page for teacher | closed | bakaqc | 2025-01-21 09:15 | 2025-01-21 09:41 | 2025-01-21 09:41 | https://github.com/lzaycoe/brainbox-frontend/pull/23
22 | add: dev <- task-17 | closed | yuhtnguyen | 2025-01-21 06:15 | 2025-01-21 06:15 | 2025-01-21 06:15 | https://github.com/lzaycoe/brainbox-frontend/pull/22
21 | WIP add: teacher layout | closed | bakaqc | 2025-01-21 02:57 | 2025-01-21 09:12 | 2025-01-21 09:12 | https://github.com/lzaycoe/brainbox-frontend/pull/21
20 | update: multiple root layout | closed | bakaqc | 2025-01-21 02:54 | 2025-01-21 03:24 | 2025-01-21 03:24 | https://github.com/lzaycoe/brainbox-frontend/pull/20
19 | update: multiple root layout | closed | bakaqc | 2025-01-21 02:53 | 2025-01-21 02:53 | 2025-01-21 02:53 | https://github.com/lzaycoe/brainbox-frontend/pull/19
15 | Implement UI for homepage | closed | htnghia1423 | 2025-01-19 03:52 | 2025-01-19 09:33 | 2025-01-19 09:29 | https://github.com/lzaycoe/brainbox-frontend/pull/15
14 | UI for homepage | closed | htnghia1423 | 2025-01-19 01:40 | 2025-01-19 03:51 | 2025-01-19 03:51 | https://github.com/lzaycoe/brainbox-frontend/pull/14
11 | Feature/task 9 | closed | htnghia1423 | 2025-01-17 02:52 | 2025-01-17 06:06 | 2025-01-17 06:06 | https://github.com/lzaycoe/brainbox-frontend/pull/11
10 | [FE] Install package needed | closed | htnghia1423 | 2025-01-16 06:24 | 2025-01-17 02:51 | 2025-01-17 02:51 | https://github.com/lzaycoe/brainbox-frontend/pull/10
8 | test: gh action & docker | closed | hardingadonis | 2025-01-16 03:30 | 2025-01-16 03:35 | 2025-01-16 03:35 | https://github.com/lzaycoe/brainbox-frontend/pull/8
7 | Feature/setup folder | closed | bakaqc | 2025-01-16 02:10 | 2025-01-16 02:43 | 2025-01-16 02:43 | https://github.com/lzaycoe/brainbox-frontend/pull/7
6 | Feature/setup folder chuong | closed | bakaqc | 2025-01-16 02:06 | 2025-01-16 02:09 | 2025-01-16 02:09 | https://github.com/lzaycoe/brainbox-frontend/pull/6

## Pull Request Backend
PR No. | Title | State | Created By | Created Date | Updated Date | Closed Date | URL
81 | update: release api v1.8.1 | closed | bakaqc | 2025-03-26 02:01 | 2025-03-26 02:38 | 2025-03-26 02:38 | https://github.com/lzaycoe/brainbox-backend/pull/81
80 | fix: err get teacher name when send email notification | closed | bakaqc | 2025-03-26 01:56 | 2025-03-26 01:57 | 2025-03-26 01:57 | https://github.com/lzaycoe/brainbox-backend/pull/80
79 | update: release api v1.8.0 | closed | bakaqc | 2025-03-25 14:06 | 2025-03-25 14:08 | 2025-03-25 14:08 | https://github.com/lzaycoe/brainbox-backend/pull/79
78 | Hotfix/all bugs chuong | closed | bakaqc | 2025-03-25 14:03 | 2025-03-25 14:04 | 2025-03-25 14:04 | https://github.com/lzaycoe/brainbox-backend/pull/78
77 | dev: merge code from main | closed | bakaqc | 2025-03-19 07:23 | 2025-03-19 13:24 | 2025-03-19 13:24 | https://github.com/lzaycoe/brainbox-backend/pull/77
76 | update: release api v1.7.5 | closed | bakaqc | 2025-03-19 07:23 | 2025-03-19 13:12 | 2025-03-19 13:12 | https://github.com/lzaycoe/brainbox-backend/pull/76
75 | update: adđ api find all users with information detail | closed | bakaqc | 2025-03-19 07:21 | 2025-03-19 07:22 | 2025-03-19 07:22 | https://github.com/lzaycoe/brainbox-backend/pull/75
74 | dev: release api v1.7.4 | closed | bakaqc | 2025-03-16 07:28 | 2025-03-16 07:34 | 2025-03-16 07:34 | https://github.com/lzaycoe/brainbox-backend/pull/74
73 | Hotfix/all bugs chuong | closed | bakaqc | 2025-03-16 07:25 | 2025-03-16 07:27 | 2025-03-16 07:27 | https://github.com/lzaycoe/brainbox-backend/pull/73
72 | dev: release api v1.7.3 | closed | bakaqc | 2025-03-15 15:25 | 2025-03-15 15:29 | 2025-03-15 15:29 | https://github.com/lzaycoe/brainbox-backend/pull/72
71 | update: api get conversation for chat gateway | closed | bakaqc | 2025-03-15 14:25 | 2025-03-15 23:35 | 2025-03-15 15:24 | https://github.com/lzaycoe/brainbox-backend/pull/71
70 | Feature/chat api chuong | closed | bakaqc | 2025-03-15 14:21 | 2025-03-15 23:35 | 2025-03-15 14:24 | https://github.com/lzaycoe/brainbox-backend/pull/70
69 | dev: release api v1.7.2 | closed | htnghia1423 | 2025-03-10 14:59 | 2025-03-10 15:00 | 2025-03-10 15:00 | https://github.com/lzaycoe/brainbox-backend/pull/69
68 | fix: err handle payment & calculate revenue | closed | htnghia1423 | 2025-03-10 14:57 | 2025-03-10 14:58 | 2025-03-10 14:58 | https://github.com/lzaycoe/brainbox-backend/pull/68
67 | fix: err handle payment & calculate revenue | closed | bakaqc | 2025-03-10 14:54 | 2025-03-10 15:03 | 2025-03-10 14:55 | https://github.com/lzaycoe/brainbox-backend/pull/67
66 | dev: release api v1.7.1 | closed | bakaqc | 2025-03-10 08:17 | 2025-03-10 11:25 | 2025-03-10 11:25 | https://github.com/lzaycoe/brainbox-backend/pull/66
65 | update: payment webhook handling | closed | bakaqc | 2025-03-10 07:55 | 2025-03-10 08:16 | 2025-03-10 08:16 | https://github.com/lzaycoe/brainbox-backend/pull/65
64 | update: handle webhook for payment | closed | bakaqc | 2025-03-10 07:52 | 2025-03-10 07:54 | 2025-03-10 07:54 | https://github.com/lzaycoe/brainbox-backend/pull/64
63 | dev: release api v1.7.0 | closed | bakaqc | 2025-03-10 03:30 | 2025-03-10 03:52 | 2025-03-10 03:52 | https://github.com/lzaycoe/brainbox-backend/pull/63
62 | [BE] Implement API handle salary for teacher | closed | bakaqc | 2025-03-10 03:27 | 2025-03-10 03:30 | 2025-03-10 03:30 | https://github.com/lzaycoe/brainbox-backend/pull/62
61 | [BE] Implement API handle salary for teacher | closed | bakaqc | 2025-03-10 03:16 | 2025-03-10 03:27 | 2025-03-10 03:27 | https://github.com/lzaycoe/brainbox-backend/pull/61
60 | dev: fix err sever conflict database column | closed | bakaqc | 2025-03-09 14:07 | 2025-03-09 14:55 | 2025-03-09 14:55 | https://github.com/lzaycoe/brainbox-backend/pull/60
59 | hotfix: err column name | closed | bakaqc | 2025-03-09 14:00 | 2025-03-09 14:06 | 2025-03-09 14:06 | https://github.com/lzaycoe/brainbox-backend/pull/59
58 | hotfix: err column name after format schemas | closed | bakaqc | 2025-03-09 13:49 | 2025-03-09 14:01 | 2025-03-09 14:00 | https://github.com/lzaycoe/brainbox-backend/pull/58
56 | dev: release api v1.6.0 | closed | bakaqc | 2025-03-04 09:34 | 2025-03-04 09:37 | 2025-03-04 09:35 | https://github.com/lzaycoe/brainbox-backend/pull/56
55 | Feature/progress api | closed | bakaqc | 2025-03-04 09:33 | 2025-03-04 09:34 | 2025-03-04 09:34 | https://github.com/lzaycoe/brainbox-backend/pull/55
54 | update: add api create progress | closed | bakaqc | 2025-03-04 09:32 | 2025-03-04 09:33 | 2025-03-04 09:33 | https://github.com/lzaycoe/brainbox-backend/pull/54
53 | dev: release api v1.5.0 | closed | bakaqc | 2025-03-02 15:06 | 2025-03-02 15:20 | 2025-03-02 15:20 | https://github.com/lzaycoe/brainbox-backend/pull/53
52 | [BE] Implement API for Realtime Chat | closed | bakaqc | 2025-03-02 14:22 | 2025-03-02 14:37 | 2025-03-02 14:37 | https://github.com/lzaycoe/brainbox-backend/pull/52
51 | [BE] Implement API for Realtime Chat | closed | bakaqc | 2025-03-02 14:13 | 2025-03-02 14:19 | 2025-03-02 14:19 | https://github.com/lzaycoe/brainbox-backend/pull/51
50 | dev: merge code from main | closed | bakaqc | 2025-03-01 13:56 | 2025-03-01 14:18 | 2025-03-01 14:18 | https://github.com/lzaycoe/brainbox-backend/pull/50
48 | update: release api v1.4.4 | closed | bakaqc | 2025-02-28 13:12 | 2025-03-01 13:55 | 2025-02-28 13:26 | https://github.com/lzaycoe/brainbox-backend/pull/48
47 | update: implement api get top teachers & get all lectures by course id | closed | bakaqc | 2025-02-28 10:54 | 2025-03-01 13:55 | 2025-02-28 13:09 | https://github.com/lzaycoe/brainbox-backend/pull/47
46 | dev: release api v1.4.3 | closed | bakaqc | 2025-02-28 04:12 | 2025-02-28 04:13 | 2025-02-28 04:13 | https://github.com/lzaycoe/brainbox-backend/pull/46
45 | add: api get courses by teacherId | closed | bakaqc | 2025-02-28 04:10 | 2025-02-28 04:11 | 2025-02-28 04:11 | https://github.com/lzaycoe/brainbox-backend/pull/45
44 | add: api get courses by teacherId | closed | bakaqc | 2025-02-28 04:09 | 2025-02-28 04:10 | 2025-02-28 04:10 | https://github.com/lzaycoe/brainbox-backend/pull/44
43 | release: release v1.4.2 | closed | hardingadonis | 2025-02-27 13:26 | 2025-02-27 13:28 | 2025-02-27 13:28 | https://github.com/lzaycoe/brainbox-backend/pull/43
42 | Hotfix/get user | closed | bakaqc | 2025-02-27 04:30 | 2025-02-27 04:36 | 2025-02-27 04:36 | https://github.com/lzaycoe/brainbox-backend/pull/42
41 | update: refactor user retrieval methods to support flexible identifier handling | closed | bakaqc | 2025-02-27 04:27 | 2025-02-27 04:28 | 2025-02-27 04:28 | https://github.com/lzaycoe/brainbox-backend/pull/41
40 | dev: release api v1.4.0 | closed | bakaqc | 2025-02-27 03:08 | 2025-02-27 03:58 | 2025-02-27 03:58 | https://github.com/lzaycoe/brainbox-backend/pull/40
39 | [BE] Implement API for Learning Course | closed | bakaqc | 2025-02-27 02:53 | 2025-02-27 03:07 | 2025-02-27 03:07 | https://github.com/lzaycoe/brainbox-backend/pull/39
38 | [BE] Implement API for Learning Course | closed | bakaqc | 2025-02-27 02:00 | 2025-02-27 03:59 | 2025-02-27 02:52 | https://github.com/lzaycoe/brainbox-backend/pull/38
37 | dev: release api v1.3.2 | closed | bakaqc | 2025-02-26 11:52 | 2025-02-26 12:11 | 2025-02-26 12:11 | https://github.com/lzaycoe/brainbox-backend/pull/37
36 | hotfix: optimize payment api & add become a teacher api | closed | bakaqc | 2025-02-26 11:37 | 2025-02-26 11:42 | 2025-02-26 11:42 | https://github.com/lzaycoe/brainbox-backend/pull/36
35 | release: release v1.3.0 | closed | hardingadonis | 2025-02-26 04:18 | 2025-02-26 04:21 | 2025-02-26 04:21 | https://github.com/lzaycoe/brainbox-backend/pull/35
34 | feat: integrate Clerk webhook handling and add svix dependency | closed | hardingadonis | 2025-02-26 04:15 | 2025-02-26 04:18 | 2025-02-26 04:18 | https://github.com/lzaycoe/brainbox-backend/pull/34
33 | feat: add get normal id for user (learn & teacher) | closed | hardingadonis | 2025-02-26 03:41 | 2025-02-26 03:44 | 2025-02-26 03:44 | https://github.com/lzaycoe/brainbox-backend/pull/33
31 | dev: merge code from main | closed | bakaqc | 2025-02-26 02:07 | 2025-02-26 02:10 | 2025-02-26 02:10 | https://github.com/lzaycoe/brainbox-backend/pull/31
30 | Hotfix/payment webhook | closed | bakaqc | 2025-02-26 02:03 | 2025-02-26 02:07 | 2025-02-26 02:07 | https://github.com/lzaycoe/brainbox-backend/pull/30
29 | hotfix: validate data test for webhook | closed | bakaqc | 2025-02-26 02:01 | 2025-02-26 02:02 | 2025-02-26 02:02 | https://github.com/lzaycoe/brainbox-backend/pull/29
28 | dev: release api v1.2.0 | closed | bakaqc | 2025-02-25 09:08 | 2025-02-25 13:54 | 2025-02-25 13:54 | https://github.com/lzaycoe/brainbox-backend/pull/28
27 | update: release api version 1.2.0 | closed | bakaqc | 2025-02-25 08:56 | 2025-02-25 09:01 | 2025-02-25 08:58 | https://github.com/lzaycoe/brainbox-backend/pull/27
26 | [BE] Implement API Payment Course | closed | bakaqc | 2025-02-25 08:53 | 2025-02-25 09:01 | 2025-02-25 09:01 | https://github.com/lzaycoe/brainbox-backend/pull/26
25 | [BE] Implement API Payment Course | closed | bakaqc | 2025-02-25 05:41 | 2025-02-25 08:52 | 2025-02-25 08:52 | https://github.com/lzaycoe/brainbox-backend/pull/25
24 | Patch for task 23 | closed | hardingadonis | 2025-02-24 06:05 | 2025-02-24 06:07 | 2025-02-24 06:07 | https://github.com/lzaycoe/brainbox-backend/pull/24
22 | release: release v1.1.0 | closed | hardingadonis | 2025-02-16 09:55 | 2025-02-16 10:20 | 2025-02-16 10:20 | https://github.com/lzaycoe/brainbox-backend/pull/22
21 | [BE] Implement CRUD for Lecture API in each Section | closed | bakaqc | 2025-02-16 07:08 | 2025-02-16 08:58 | 2025-02-16 08:55 | https://github.com/lzaycoe/brainbox-backend/pull/21
20 | add: crud api for `lecture` & optimize code | closed | bakaqc | 2025-02-16 03:53 | 2025-02-16 08:25 | 2025-02-16 07:07 | https://github.com/lzaycoe/brainbox-backend/pull/20
19 | [BE] Implement CRUD for Session API in each Course | closed | bakaqc | 2025-02-15 13:39 | 2025-02-16 08:24 | 2025-02-15 13:43 | https://github.com/lzaycoe/brainbox-backend/pull/19
18 | add: crud api for `session` | closed | bakaqc | 2025-02-15 07:51 | 2025-02-15 13:43 | 2025-02-15 13:39 | https://github.com/lzaycoe/brainbox-backend/pull/18
15 | [BE] implement CRUD for Courses API | closed | bakaqc | 2025-02-15 00:39 | 2025-02-15 01:23 | 2025-02-15 01:23 | https://github.com/lzaycoe/brainbox-backend/pull/15
14 | add: crud api for `course` | closed | bakaqc | 2025-02-14 14:47 | 2025-02-15 00:38 | 2025-02-15 00:38 | https://github.com/lzaycoe/brainbox-backend/pull/14
12 | release: release v1.0.2 | closed | hardingadonis | 2025-02-12 04:09 | 2025-02-12 04:12 | 2025-02-12 04:12 | https://github.com/lzaycoe/brainbox-backend/pull/12
11 | release: release v1.0.1 | closed | hardingadonis | 2025-02-05 03:29 | 2025-02-05 05:31 | 2025-02-05 03:33 | https://github.com/lzaycoe/brainbox-backend/pull/11
10 | release: release v1.0.0 | closed | hardingadonis | 2025-01-26 07:47 | 2025-01-26 15:19 | 2025-01-26 15:19 | https://github.com/lzaycoe/brainbox-backend/pull/10
9 | done: finish task 3 & 4 | closed | hardingadonis | 2025-01-26 07:46 | 2025-01-26 08:33 | 2025-01-26 08:33 | https://github.com/lzaycoe/brainbox-backend/pull/9
8 | done: implement clerk strategy for learners & teachers | closed | hardingadonis | 2025-01-26 07:42 | 2025-01-26 09:39 | 2025-01-26 08:32 | https://github.com/lzaycoe/brainbox-backend/pull/8
7 | done: implement local strategy authentication for admin | closed | hardingadonis | 2025-01-21 03:56 | 2025-01-21 04:35 | 2025-01-21 04:35 | https://github.com/lzaycoe/brainbox-backend/pull/7
6 | finish: done #4 | closed | hardingadonis | 2025-01-20 02:27 | 2025-01-20 03:22 | 2025-01-20 03:22 | https://github.com/lzaycoe/brainbox-backend/pull/6
5 | Implement CURD for admin | closed | hardingadonis | 2025-01-19 16:13 | 2025-01-20 02:02 | 2025-01-20 02:02 | https://github.com/lzaycoe/brainbox-backend/pull/5
1 | update: update trigger for `Release and Publish` workflow | closed | hardingadonis | 2025-01-08 16:11 | 2025-01-08 16:17 | 2025-01-08 16:17 | https://github.com/lzaycoe/brainbox-backend/pull/1